## Project Timeline
PROJECT TIMELINE
FaultTrack ALM |  |  |  | DCOM Engineering, LLC
Project Details
DATE | MILESTONE | POSITION | BASELINE
2013-01-01 | Project Start | 25 | 1
2013-06-01 | Basic Project Functionality | 15 | 1
2013-07-01 | Basic User Functionality | -10 | 1
2013-08-01 | Bootstrapper | 10 | 1
2013-08-07 | Project Assessment | -15 | 1
2013-09-01 | TBA | 25 | 1
2013-10-01 | TBA | 25 | 1
2013-11-01 | TBA | 25 | 1
2013-12-01 | System Testing and Refactoring | -10 | 1
2014-01-31 | Internal Release | 10 | 1
2014-02-07 | Project Assessment | -15 | 1
2014-03-01 |  |  | 1
2014-04-01 |  |  | 1
2014-05-01 |  |  | 1
2014-06-01 |  |  | 1
2014-07-01 |  |  | 1
2014-08-01 |  |  | 1
2014-09-01 |  |  | 1
2014-10-01 |  |  | 1
2014-11-01 |  |  | 1
2014-12-01 |  |  | 1
2015-01-31 | Public Release | 25 | 1